## Sheet 1
Table 1
Use this sheet to track your time while creating your projects. It is important that all details are meticulously included for a better understanding of the time that you took to create the project. Also in the last row include the total number of hours. You can include as many rows and activities as required by your project |  |  |  |  | Project details and Educator details
Upload this tracking sheet on or before Nov 10th to consolidate the engagement hours to be sent to the ops team. Billable time is 24 hours for this duration Use the link below to upload your tracking sheet in EXCEL SHEET format only. Max size 500kb https://bit.ly/Parul-University-Upload-Tracking-sheet-for-Nov1st-to-Nov10th
Date | Title of the activity | Description | List of activities | Time taken in hours |  |  | First Name | Last Name
2024-11-01 | User Interface Design and Initial Templates | Implement the foundational frontend layout using HTML and CSS. | 1. Create base templates with sections for header, footer, and navigation. 2: Ensure the site is responsive by testing the layout on different screen sizes. | 4 | Project details and Educator details | Name of the educator | Rudra | Joshi
2024-11-02 | Time Entry Form Implementation | Develop the time entry forms | 1: Create the time entry form with fields for task name, project, start and end times. 2: Implement backend views for handling time entries, including form validation | 4 |  | Contact Number of the educator | 8320296918
2024-11-03 | Contact Form and Inquiry Management | Develop a contact form for user inquiries and set up backend management for inquiries | 1: Implement a contact form with fields for name, email, subject, and message. 2: Configure backend views to save inquiries to the database. 3: Create a basic admin view to review inquiries and manage responses. | 4 |  | Email id of the educator | rudrajoshi1810@gmail.com
2024-11-04 | Timer Feature and Time Validation | Added user engagement tools, including a newsletter form and admin controls. | 1: Add a timer functionality for automatic time tracking. 2: Implement validation to ensure start time is before end time. | 4 |  | Title of the project | Timesheet Tracking Application
2024-11-05 | Dashboard and Time Summary Display | Enhance site performance and user experience. | 1: Integrate filters for viewing entries by project or time period. 2: Develop a dashboard to show a summary of total hours by project. | 4 |  | Link to your Github repository | https://github.com/Zen-trepreneur/Timesheet
2024-11-06 | Deployment Preparation and Documentation | Prepared for deployment and complete project documentation. | 1: Finalize production configurations in settings.py, such as database, static files, and security settings. 2: Write README documentation, including installation instructions, feature breakdown, and usage guide | 4 |  | Domain / Discipline | Full Stack Development
[6 empty] | Platforms used | Python, Django
[6 empty] | Nimbus Workspace ID if you have used Nimbus | NA
Total number of hours |  | 24